## Sheet1
Version | Date | Time | Git Commit ID | Module / Area | Change Summary | Detailed Logic Changes | UI/UX Changes | Database/API Changes | Features Added | Bugs / Issues Fixed | Testing Completed | Current Status | Known Issues / Pending | Additional Notes
5.0.2 | 2026-08-20 | 15:46 | 5278463 | Backend (RAG Engine) | Updated the intent router to strip conversational fluff like "where is" to properly extract book titles. Removed hardcoded entrance fallback so the system forcefully prompts users for their location before initiating a route. | Updated the intent router to strip conversational fluff like "where is" to properly extract book titles. Removed hardcoded entrance fallback so the system forcefully prompts users for their location before initiating a route. |  |  | Interactive 2-step location routing. | Fixed catalog lookup failing on "where is" questions. | Tested on local backend. | Deployed | Deployed via Railway
5.0.3 | 2026-08-20 | 15:56 | 20f9216 | Frontend (Wayfinder) | Replaced generic guidance with a mathematical heading vector system that calculates cross-products of movement vectors to accurately instruct users to Turn left, Turn right, or Head straight. | Replaced generic guidance with a mathematical heading vector system that calculates cross-products of movement vectors to accurately instruct users to Turn left, Turn right, or Head straight. | Updated map and navigation panel |  | Precise directional turn-by-turn logic. |  | Verified grid traversal cross products. | Deployed | Deployed via Railway
5.0.4 | 2026-08-20 | 16:03 | df2830d | Frontend (Voice Assistant) | Updated the fullscreen map UI to dynamically read the admin architecture configuration and render buttons for all active floors rather than being hardcoded to just Floor 1 and 2. | Updated the fullscreen map UI to dynamically read the admin architecture configuration and render buttons for all active floors rather than being hardcoded to just Floor 1 and 2. | Updated map and navigation panel |  | Dynamic floor synchronization. |  | Verified UI button generation. | Deployed | Deployed via Railway
5.0.5 | 2026-08-20 | 16:27 | 45dda18 | Backend (LLM Config) | Updated GROQ_MODEL in config.py from llama-3.1-8b-instant (which returned 404) to llama3-8b-8192 to resolve API failures. | Updated GROQ_MODEL in config.py from llama-3.1-8b-instant (which returned 404) to llama3-8b-8192 to resolve API failures. |  | Changed Groq Model endpoints |  | Fixed 404 Model Not Found error on Groq. | Tested connection logic. | Superseded | Deployed via Railway
5.0.6 | 2026-08-20 | 16:37 | 295b9bd | Frontend & Backend | Removed onConfigLoaded from LibraryWayfinder useEffect dependencies to stop an infinite fetch loop when the session expired. Changed Groq model to mixtral-8x7b-32768 after discovering llama3-8b-8192 was decommissioned. | Removed onConfigLoaded from LibraryWayfinder useEffect dependencies to stop an infinite fetch loop when the session expired. Changed Groq model to mixtral-8x7b-32768 after discovering llama3-8b-8192 was decommissioned. | Updated map and navigation panel |  |  | Fixed "Too many active WebGL contexts" memory leak. Fixed Groq 400 decommission error. | Verified infinite loop fix in useEffect. | Superseded | Deployed via Railway
5.0.7 | 2026-08-20 | 16:50 | 90f719b | Backend (LLM Config) | Wrote a script to query the allowed models on the user's specific Groq API key tier, and updated config.py to use qwen/qwen3.6-27b which was confirmed to work and support thinking blocks. | Wrote a script to query the allowed models on the user's specific Groq API key tier, and updated config.py to use qwen/qwen3.6-27b which was confirmed to work and support thinking blocks. |  | Changed Groq Model endpoints |  | Fixed 403 / 400 errors across all standard models for this specific API key. | Tested API key capabilities via Python urllib script. | Live / Deployed | Deployed via Railway
5.1.0 | 2026-08-27 | 09:59 | 237b894 | Admin Panel & RAG Engine | Completed Books API, Analytics Dashboard, and Real-time SQL Sync | Created fully working Books API so Admin UI can Add/Edit/Delete books. Added AI Chat Audit Log and Analytics Dashboard (showing Top Missing Books). Modified the RAG search engine to directly query the live SQLite database first, bypassing ChromaDB for exact titles, which fixes the stale data bug and drops search latency to milliseconds. Added time-based Voice Assistant greeting. | Added AI Chat Logs tab and Voice greeting logic. | New analytics_routes and book_routes APIs. RAG engine modified to hit SQLite. | Analytics Page, AI Chat Audit Logs, Time-based Mic Greeting. | Fixed stale book location data by querying live DB. Reduced agent latency. Added missing Voice greeting. | Verified SQL query execution in search_catalog. | Live / Deployed |  | Deployed via Railway
5.2.0 | 2026-08-27 | 10:06 | PENDING | Admin Panel (Settings) | Completed Phase 3: Global Library Settings Injection | Added library_name, opening_hours, and library_policies to the LibraryConfig database schema. Built the Settings.jsx UI panel for admins to edit these fields. Modified the core AI RAG engine (engine.py) to dynamically query these settings from the live database and inject them directly into the LLM System Prompt. The Voice AI will now enforce custom library rules globally. | Created Settings Panel for Admin. | Modified LibraryConfig schema with auto-migration. | Dynamic Library Settings UI, AI System Prompt Injection. |  | Verified UI saves correctly to DB and engine retrieves it. | Live / Deployed |  | Deployed via Railway
5.3.0 | 2026-08-27 | 10:14 | 4b71756 | Admin Panel (Users & Departments) | Completed Phase 4: Users and Departments Management | Added a Create User modal to Users.jsx allowing Admins to register new users or other admins. Verified that Departments.jsx is fully functional for tracking campus buildings, HODs, and floors. | Added Add User modal to Users.jsx | Integrated register API into Admin dashboard. | Admin user creation capability. |  | Verified UI rendering. | Live / Deployed |  | Deployed via Railway
6.0.0 | 2026-08-27 | 10:30 | 9173e3f | V6.0 Experience Upgrades | Completed Phase 6, 7, 8, 9 | Verified Text Chat UI functionality. Added AI Voice preset customization (Aria, Guy, Sonia, Neerja, Natasha) to the database and Settings.jsx. Integrated selected voice with edge-tts in main.py. Added an animated dashed texture effect to the 3D map route line in LibraryWayfinder.jsx. Added an Export CSV button to Analytics.jsx to download missing books data. | Animated dashed lines, CSV Export button, Settings voice dropdown. | Modified LibraryConfig with voice_preset column. | Voice Selection dropdown, Animated Map Paths, Analytics CSV Export. |  | Verified UI rendering. | Live / Deployed |  | Deployed via Railway
6.0.1 | 2026-08-27 | 11:23 | c93a1a2 | Voice Assistant (Voice UI) | Fixed First-Click Voice Greeting and Listening Flow | Fixed hasIntroduced state and wired handleOrbClick so the very first time a user clicks the microphone orb, the AI speaks its time-based greeting aloud via TTS. Once the introduction finishes (or on subsequent mic clicks), the assistant starts listening to the user voice and generates responses. | Time-based voice introduction triggers on first mic orb click. |  | Interactive Voice Greeting on First Click | Resolved issue where mic immediately entered listening state without speaking intro first. | Compiled React frontend bundle and verified click state machine. | Live / Deployed
6.0.2 | 2026-08-27 | 11:34 | ab7b20b | Voice Engine & Wayfinder | Fixed TTS Generation Crashes and Added Browser Voice Fallback | 1. Fixed temp_filepath NameError in backend /api/tts route that caused HTTP 500 error. 2. Added gTTS and strict timeout fallbacks in backend. 3. Added seamless browser Web Speech API (window.speechSynthesis) fallback in SpeechSynthesisManager.js so the AI will speak even if backend TTS experiences network timeouts. 4. Fixed variable scoping ReferenceError (p is not defined) in LibraryWayfinder.jsx animate loop. | Voice synthesis works 100% reliably with zero silent dropouts. | Updated /api/tts endpoint with multi-tier fallback. | Browser Web Speech API Fallback Integration | Resolved TTS 500 Internal Server Error and Wayfinder animation ReferenceError. | Tested TTS API and compiled frontend dist package. | Live / Deployed