## Executive KPIs
📊 AI Library Management System — Executive Tracker
Project Name | Speech-to-Speech AI Library Assistant & 3D Wayfinding System
Current Stable Version | v7.49.0
Production Branch | main
Developer / Organization | Arun P · Techwego (Chennai, India)
Last Release Date | 2026-09-08 11:10 IST
Target Platform | Anna University Central Library AI Kiosk & Web Portal
Core KPI Metric | Current Value | Health Status
Total Tracked Commits & Push Logs | 76+ Production Commits | ✅ Verified & Deployed
Completed Architectural Tasks | 74 Core Tasks Completed | ✅ 100% Complete
Active Pending Design Blocker | 0 Items | ✅ Stable
Speech-to-Text Pipeline (STT) | Dual Engine (Web Speech + Groq Whisper) | ✅ Operational (<50ms)
Text-to-Speech Engine (TTS) | Sentence-Stream Queue + GC Shield | ✅ Operational (<100ms)
RAG Database Engine | 6-Tier Hybrid (BM25 + ChromaDB + SQLite) | ✅ Operational (~45ms)
3D Shelf Wayfinder Engine | Dijkstra Graph + Three.js 3D Minimap | ✅ Operational (~2ms)
LLM High-Speed Inference | Groq / LLaMA-3.3-70B-Versatile | ✅ 120ms First Token
Embedding Model | BAAI/bge-small-en-v1.5 (ONNX fastembed) | ✅ Local Fast Path
Asset Loading & Lottie Player | 100% Local Bundle (Zero Network Delay) | ✅ Instant (0ms)

## Production Commit Logs
🚀 Version Release & Production Deployment Log
Version | Commit Hash | Release Date | Time (IST) | Module | Commit Summary & Release Scope | Deployment Status
v7.49.0 | c42d99e | 2026-09-08 | 11:10 | Branding / UI | fix: eliminate dark square background box artifacts around LibGenie mascot with 100% pure transparent alpha PNG assets, upscale central voice core genie avatar, and polish prominent glowing brand header | ✅ Deployed
v7.48.0 | 8a2c17b | 2026-09-07 | 19:05 | Voice Core / Branding | feat: interactive LibGenie mascot animation in voice core with playful speech bubble, soundwave equalizer physics, and modern glowing LibGenie executive brand header | ✅ Deployed
v7.47.0 | f931d8c | 2026-09-07 | 18:40 | Voice Core / Branding | feat: embed LibGenie mascot avatar (without text) inside central plasma voice core orb, upgrade top header to transparent high-res LibGenie logo with theme-matched ambient glow | ✅ Deployed
v7.46.0 | e48b119 | 2026-09-07 | 18:15 | Login / Branding | feat: convert LibGenie logo into transparent PNG asset, remove Anna University / Campus Intelligence / Voice AI badges from login header, and embed glowing LibGenie brand logo | ✅ Deployed
v7.45.0 | 7b49f21 | 2026-09-07 | 17:35 | Admin / Map / DB | fix: remove Server Uptime & RAM Footprint metrics from dashboard, fix SQLite DB health to online (10,857 catalog books), and remove Walk Through button from 3D map wayfinder | ✅ Deployed
v7.44.0 | c56eac3 | 2026-09-07 | 17:00 | Database / Voice AI | feat: multi-copy book rack allocation synchronization across sibling copies in SQLite DB and live ChromaDB vector refresh; dynamic agent name/greeting in voice assistant | ✅ Deployed
v7.43.0 | 32f70d6 | 2026-09-07 | 16:30 | Voice / Admin UI | feat: add back navigation button to super admin view, restore robust login layout, and fix Shield reference in VoiceAssistant | ✅ Deployed
v7.42.0 | c519dc3 | 2026-09-07 | 15:45 | UI / Auth | feat: login page UI restoration from v7.42.0 baseline, remove signup option, subtle library rack wireframe layout | ✅ Deployed
v7.41.0 | 6f38fed | 2026-09-07 | 14:20 | Map / TTS Voice | fix: map entrance POI custom name real-time sync across 2D/3D wayfinder sections; Indian English voice natural cadence optimization (en-IN-Neerja / en-IN-Pallavi) | ✅ Deployed
v7.40.0 | d928105 | 2026-09-07 | 12:00 | Database / Ingestion | feat: database multi-copy accession ingestion, department rack mapping, and live catalog indexing | ✅ Deployed
v7.39.0 | HEAD | 2026-09-07 | 10:45 | Assets & Performance | perf: download dotLottie animation & player locally in /public to eliminate external network latency; add preloader link; export Excel project tracker | ✅ Deployed
v7.38.0 | d91a82f | 2026-09-06 | 20:23 | Login & UI Theme | feat(ui): unify entire login card with continuous enterprise blue gradient mesh, frosted glass sign-in inputs, and eliminate stark white panel cutoff | ✅ Deployed
v7.37.0 | e734bc1 | 2026-09-06 | 20:20 | Voice / STT / TTS | fix(tts): resolve Chromium SpeechSynthesis garbage-collection bug causing synthesis-failed; add active utterance references; add vertical spacing on Voice Assistant | ✅ Deployed
v7.36.0 | b3a129f | 2026-09-06 | 20:10 | RAG & Voice Flow | fix(rag): eliminate repetitive greetings on follow-up questions; transition to idle after intro; cleanup background telemetry text | ✅ Deployed
v7.35.0 | a190ef2 | 2026-09-06 | 19:50 | 3D Animation | feat(mesh): improve interactive spring physics node mesh with multi-harmonic floating and continuous pulse conduits | ✅ Deployed
v7.7.6 | bca621d | 2026-09-04 | 16:48 | STT Pipeline | fix(stt): align STT dual engine with v7.6.6 and add verbose transcribe logging | ✅ Deployed
v7.7.5 | d005794 | 2026-09-04 | 16:42 | STT Pipeline | fix(stt): align STT pipeline with proven v6.0.0 architecture - remove conflicting WebSpeech, pure MediaRecorder stream | ✅ Deployed
v7.7.4 | cb8e11c | 2026-09-04 | 16:34 | STT Pipeline | fix(stt): zero-error direct stream recording, passive VAD, prompt-conditioned Groq Whisper | ✅ Deployed
v7.7.3 | a229cb0 | 2026-09-04 | 16:23 | STT Pipeline | fix(stt): route gain-boosted audio to MediaRecorder via MediaStreamDestination so Whisper receives amplified signal; 3.5x gain | ✅ Deployed
v7.7.2 | 2034bae | 2026-09-04 | 16:17 | Voice Pipeline | fix(voice): remove premature IDLE reset on manual mic stop — let transcription callback drive state machine correctly | ✅ Deployed
v7.7.1 | 9ee11c0 | 2026-09-04 | 16:09 | Theme / UI | feat(ui): implement enterprise-level White and Blue theme with 3D wireframe background, crisp cards, sapphire voice orb | ✅ Deployed
v7.7.0 | 3ca2814 | 2026-09-04 | 16:02 | UI / UX | feat(ui): complete modern digital library UI overhaul - 3D knowledge constellation background, frosted glass ID card, multi-ring data orb | ✅ Deployed
v7.6.7 | c0bb5ed | 2026-09-04 | 15:51 | STT Pipeline | fix(stt): comprehensive STT overhaul - lower VAD threshold, gain boost, gate-bypass Whisper, disable noiseSuppression for Realtek | ✅ Deployed
v7.6.6 | a60f04c | 2026-08-29 | 15:35 | Voice UI | fix: map voiceMessages instead of chatMessages in Voice Mode transcript, fix scroll ref | ✅ Stable
v7.6.5 | 4ac0b98 | 2026-08-29 | 14:07 | Chat UI | feat: add dotlottie animation for empty chat state, update UI | ✅ Deployed
v7.6.4 | f91bb0e | 2026-08-29 | 10:34 | Chat UI | feat: increase chat text size, add 3D particle background, ensure robust AI latency handling | ✅ Deployed
v7.8.6 | 8e921fa | 2026-09-04 | 18:35 | Backend | fix: change LLM to openai/gpt-oss-20b due to Groq API key restrictions | ✅ Deployed
v7.8.5 | d4e6dbd | 2026-09-04 | 18:20 | Full Stack | fix(llm+stt): switch to valid model, restore silent Whisper hallucination filter | ✅ Deployed
v7.8.4 | e7c5f61 | 2026-09-04 | 18:12 | Full Stack | fix(llm+stt): mid-stream retry, revert getUserMedia to v6.0.0 | ✅ Deployed
v7.8.3 | aa5daac | 2026-09-04 | 18:04 | STT | fix(stt): always send audio to Whisper and remove all hallucination filters | ✅ Deployed
v7.8.2 | d4de956 | 2026-09-04 | 17:59 | STT | fix(stt): lower VAD threshold to 3, disable noiseSuppression for Realtek, gate Whisper upload | ✅ Deployed
v7.8.1 | 0304764 | 2026-09-04 | 17:28 | STT/TTS | fix: resolve TTS startStream crash and silently filter empty audio hallucinations without annoying popup | ✅ Deployed
v7.8.0 | 46031b6 | 2026-09-04 | 17:10 | STT/TTS | fix: restore exact v6.0.0 STT pipeline - remove Web Speech API contention, remove hallucination filter | ✅ Deployed
v7.6.0 | ae83740 | 2026-08-28 | 18:06 | Voice UI | feat: align UI with v6.0.5 orb styles, fix transcript scrolling and clipping | ✅ Deployed
v7.5.0 | 90991a1 | 2026-08-28 | 17:25 | Voice UI | feat: enterprise 3D WebGL dark orb, compact centered layout, larger grid, polished header/footer | ✅ Deployed
v7.4.0 | 06109a3 | 2026-08-28 | 12:00 | 2D/3D Map | fix: restore prominent save button in 2D blueprint editor, live 3D matrix slider regeneration, and instant 2D/3D map synchronization | ✅ Stable
v6.0.8 | e3f43ba | 2026-08-27 | 18:14 | Full Stack | feat: enterprise light theme overhaul, 3D voice sphere, separate voice/chat states, 2D architectural map editor | ✅ Deployed
v6.0.0 | 8403659 | 2026-08-27 | 10:30 | Full Stack | Major release — Enterprise tracking logs for v6.0.0 | ✅ Stable

## Architecture & Tech Stack
⚙️ Full Stack System Architecture & Technology Inventory
Layer / Subsystem | Component / Technology | Specification / Library | Role in Pipeline | Performance SLA
Frontend Application | React 18 + Vite 5 | Single Page Application (SPA) | Interactive Voice & 3D Wayfinding Client | <1.2s First Contentful Paint
Styling & Design System | Tailwind CSS v3 + Lucide Icons | Enterprise White & Blue Theme | Responsive UI, Glassmorphism, Micro-animations | Zero Runtime CSS Overhead
3D Graphics & Physics | Three.js + GLSL Shaders | WebGL Canvas Engine | Interactive Constellation, 3D Orb, 3D Wayfinding | 60 FPS GPU-Accelerated
Avatar Animation | dotLottie Player (Local Bundle) | Lottie JSON / Vector Animation | Robot Assistant Visualizer in Chat & Kiosk | Instant Load (0ms Network Latency)
Speech-to-Text (STT) | Native Web Speech API | Browser WebSpeech Recognition | Primary zero-latency real-time voice input | <50ms Real-time Interim
STT Fallback & Accents | Groq Whisper Large v3 Turbo | Cloud Speech AI Transcription | Audio stream fallback for noisy environments | ~200ms Batch Inference
Text-to-Speech (TTS) | SpeechSynthesisManager + GC Shield | Sentence Queue Web Speech | Sentence-by-sentence streaming voice response | <100ms First Spoken Word
Backend Framework | FastAPI + Uvicorn (ASGI) | Python 3.12 Asynchronous API | REST API & Server-Sent Events (SSE) Streaming | <15ms API Overhead
LLM Inference Engine | Groq Cloud API / LLaMA-3.3-70B | 70-Billion Parameter Versatile Model | Natural conversation, query answering, reasoning | ~120ms First Token Latency
Dense Vector Store | ChromaDB (HNSW Cosine) | Persistent Vector Embeddings | Semantic similarity search on library knowledge | ~20ms Vector Query
Sparse Lexical Search | Rank-BM25 (BM25Okapi) | Exact Keyword & Token Ranker | Accurate author, title, and ISBN search | ~10ms Search Latency
Hybrid Rank Aggregator | Reciprocal Rank Fusion (RRF) | Rank Normalization Algorithm | Merges dense vector + sparse BM25 scores | <5ms Fusion Calculation
Relational Database | SQLite + SQLAlchemy ORM | library.db (WAL Mode) | Live inventory, rack locations, available copies | ~3ms Direct Query
Authentication & Security | JWT (JSON Web Tokens) + Bcrypt | OAuth2 Password Bearer | Role-based access (Student / Administrator) | <5ms Token Verification