## Update Tracking Log
Date | Time | Commit_ID | Version | Module | What_Changed | What_Fixed | New_Features | Backend_Changes | Workflow_Changes | Testing_Completed | Status | Pending_Work
2026-08-27 | 11:24 IST | aec26e8 | v6.0.1 | Voice Pipeline, STT/TTS | Fixed voice synthesis initialization and error handlers in Edge/Chromium. | TTS engine failing on page load without user interaction. | Web Speech API fallback engine with resilient audio synthesis. | None | Speech manager waits for onvoiceschanged before triggering greeting. | Audio playback verified in Edge & Chrome. | Completed & Pushed | None
2026-08-27 | 11:42 IST | beff0c0 | v6.0.3 | RAG Engine, Book Database | Replaced static caching with real-time live database synchronization on all RAG queries. | Out-of-sync rack locations and newly added books not resolving in vector search. | Live DB fallback vector matching. | Updated /api/chat query processor to query SQLAlchemy books table directly. | Book searches now query both live database and vector index. | FastAPI test suite passed 100%. | Completed & Pushed | None
2026-08-27 | 12:15 IST | d46f031 | v6.0.5 | AI Chat, Wayfinder Routing | Eliminated hallucinated rack routes on general conversation questions. | AI returning accidental map routes when users asked non-location questions. | Explicit location query intent detector. | Strict JSON schema validation on tool calls in Groq engine. | Map route only triggered when explicit book title or rack code is requested. | Verified 20+ general and navigational query prompts. | Completed & Pushed | None
2026-08-27 | 12:58 IST | 769ed38 | v6.0.7 | Admin Book Catalog | Handled unique constraint checks and available copies editing. | ISBN unique constraint error when updating existing book metadata. | Available copies live counter & quick edit modal. | Updated PUT /api/admin/books/{id} to exclude current book ID from ISBN uniqueness check. | Admins can edit book titles, authors, and rack assignments without ISBN collision. | Admin CRUD tested with multiple duplicate ISBN scenarios. | Completed & Pushed | None
2026-08-27 | 18:14 IST | e3f43ba | v7.0.0 | Global Theme, 3D Wayfinder, 2D Floor Plan Editor, Netlify | Complete enterprise light theme migration (white & light blue), 2D drag-and-drop blueprint editor, separate Voice/Chat state isolation. | Dark theme contrast issues; voice transcripts cluttering text chat; lack of visual floor plan customizer. | FloorPlanEditor2D component with 1m grid snapping, 3D multi-floor wayfinder with Catmull-Rom route tubes, Netlify deployment configuration. | Added custom_layout column to LibraryConfig model and admin architecture endpoint. | Voice Mode and Chat Mode operate on independent message state arrays. | Full frontend Vite build verified; 3D Three.js rendering confirmed. | Completed & Pushed | None
2026-08-28 | 10:24 IST | 007c43d | v7.1.0 | Admin Voice Settings, TTS Synthesis | Synchronized admin-selected voice across entire session; added Indian female voice catalog; live audio preview. | Greeting played in default male voice before selected voice was applied. | Curated Indian female voice catalog (Neerja, Swara, Heera, Priya, Kavya), international voices, and system voice scanner. | voice_preset persisted in LibraryConfig model. | VoiceAssistant fetches architecture voice config on mount before triggering initial greeting. | Tested audio sample preview and cross-browser speech synthesis. | Completed & Pushed | None
2026-08-28 | 11:21 IST | 19b15bc | v7.2.0 | UI Design, Voice Orb, Navigation & Auth | Enterprise-level UI overhaul with gradient buttons, glassmorphic nav bar, shimmer login page, and plasma GLSL orb. | Plain flat buttons in wayfinder and navbar; mic icon overlay on 3D voice sphere. | 3-octave fractal GLSL simplex noise plasma orb, shimmer submit buttons, gradient chat bubbles, glassmorphic profile pill. | None | The 3D sphere deforms organically with real-time sound amplitude without needing any 2D mic icons. | Vite production build succeeded in 10.75s with 0 errors. | Completed & Pushed | None
2026-08-28 | 11:36 IST | 1dd987a | v7.3.0 | Animation Engine, Visual Equalizers | Comprehensive dynamic animation overhaul with interactive constellation mesh background and live equalizer soundwaves. | Static look and feel; added rich floating motion physics and active sound visualizer bars. | AnimatedBackground constellation canvas, live audio soundwave bars for Listening / Speaking states, button specular shimmer sweeps. | None | Interactive hover physics applied to all cards and buttons across the portal. | Vite build passed in 9.92s. | Completed & Pushed | None
2026-08-28 | 12:00 IST | 06109a3 | v7.4.0 | 2D/3D Architecture Synchronization | Synchronized 2D blueprint editor with 3D map viewport; restored prominent floating save buttons; live matrix slider updates. | 3D map falling back to synthetic grid instead of custom 2D layout; missing save button on small viewports; slider changes not reflecting in 3D preview. | Persistent floating [Save Blueprint & Apply to 3D Map] action bar, live 3D matrix regeneration on slider move, dynamic 3D slab scaling. | None | Any change made in 2D blueprint or slider matrix immediately updates 3D map coordinates in real time. | Vite build passed in 7.27s; Dijkstra pathfinding verified through custom 2D layouts. | Completed & Pushed | None