## Sheet1
Version (Major.Minor.Build) | Release Date | Git Commit Range | Major Changes Overview | Functional / Logic Changes | UI/UX Changes | Database / API / Backend Changes | Bugs / Issues Fixed | QA / Testing Status | Current Status | Limitations / Pending Work | Version | Date | Git Push ID | Major Changes | Functional Changes | Database/API Changes | Bugs Fixed | Testing Status | Notes
5.0.2 | 2026-08-20 | 5278463 | Fixed catalog search bug and updated location routing logic. | Updated the intent router to strip conversational fluff like "where is" to properly extract book titles. Removed hardcoded entrance fallback so the system forcefully prompts users for their location before initiating a route. |  |  | Fixed catalog lookup failing on "where is" questions. | Tested on local backend. | Deployed | Deployed via Railway
5.0.3 | 2026-08-20 | 20f9216 | Added GPS-style turn-by-turn navigation. | Replaced generic guidance with a mathematical heading vector system that calculates cross-products of movement vectors to accurately instruct users to Turn left, Turn right, or Head straight. | Updated map and navigation panel |  |  | Verified grid traversal cross products. | Deployed | Deployed via Railway
5.0.4 | 2026-08-20 | df2830d | Dynamic floor switcher buttons in 3D Map. | Updated the fullscreen map UI to dynamically read the admin architecture configuration and render buttons for all active floors rather than being hardcoded to just Floor 1 and 2. | Updated map and navigation panel |  |  | Verified UI button generation. | Deployed | Deployed via Railway
5.0.5 | 2026-08-20 | 45dda18 | Changed Groq Model ID. | Updated GROQ_MODEL in config.py from llama-3.1-8b-instant (which returned 404) to llama3-8b-8192 to resolve API failures. |  | Changed Groq Model endpoints | Fixed 404 Model Not Found error on Groq. | Tested connection logic. | Superseded | Deployed via Railway
5.0.6 | 2026-08-20 | 295b9bd | Fixed WebGL leak and updated Groq model. | Removed onConfigLoaded from LibraryWayfinder useEffect dependencies to stop an infinite fetch loop when the session expired. Changed Groq model to mixtral-8x7b-32768 after discovering llama3-8b-8192 was decommissioned. | Updated map and navigation panel |  | Fixed "Too many active WebGL contexts" memory leak. Fixed Groq 400 decommission error. | Verified infinite loop fix in useEffect. | Superseded | Deployed via Railway
5.0.7 | 2026-08-20 | 90f719b | Final Groq Model alignment for API key. | Wrote a script to query the allowed models on the user's specific Groq API key tier, and updated config.py to use qwen/qwen3.6-27b which was confirmed to work and support thinking blocks. |  | Changed Groq Model endpoints | Fixed 403 / 400 errors across all standard models for this specific API key. | Tested API key capabilities via Python urllib script. | Live / Deployed | Deployed via Railway
[5 empty] | Added AI Chat Logs tab and Voice greeting logic. |  |  |  | Live / Deployed |  | 5.1.0 | 2026-08-27 | 237b894 | Completed Books API, Analytics Dashboard, and Real-time SQL Sync | Created fully working Books API so Admin UI can Add/Edit/Delete books. Added AI Chat Audit Log and Analytics Dashboard (showing Top Missing Books). Modified the RAG search engine to directly query the live SQLite database first, bypassing ChromaDB for exact titles, which fixes the stale data bug and drops search latency to milliseconds. Added time-based Voice Assistant greeting. | New analytics_routes and book_routes APIs. RAG engine modified to hit SQLite. | Fixed stale book location data by querying live DB. Reduced agent latency. Added missing Voice greeting. | Verified SQL query execution in search_catalog. | Deployed via Railway
[5 empty] | Created Settings Panel for Admin. |  |  |  | Live / Deployed |  | 5.2.0 | 2026-08-27 | PENDING | Completed Phase 3: Global Library Settings Injection | Added library_name, opening_hours, and library_policies to the LibraryConfig database schema. Built the Settings.jsx UI panel for admins to edit these fields. Modified the core AI RAG engine (engine.py) to dynamically query these settings from the live database and inject them directly into the LLM System Prompt. The Voice AI will now enforce custom library rules globally. | Modified LibraryConfig schema with auto-migration. |  | Verified UI saves correctly to DB and engine retrieves it. | Deployed via Railway